## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | time axis 2018-02-20 to 2018-04-17
[63 empty] | 58 | 59 | 60 | time axis 2018-02-20 to 2018-04-17
Learn Express | 1 | 4 |  |  | 0%
Learn Socket.io | 5 | 2 |  |  | 0%
Learn TypeScript | 1 | 6 |  |  | 0%
Design Document | 7 | 7 |  |  | 0%
Define API | 14 | 7 |  |  | 0%
Define Model | 14 | 7 |  |  | 0%
Client UI | 14 | 7 |  |  | 0%
Client Accept User Input | 21 | 4 |  |  | 0%
Transmit User Input to Server | 25 | 2 |  |  | 0%
Server Accept User Input | 27 | 2 |  |  | 0%
Server 2 body orbital physics (passive objects) | 21 | 7 |  |  | 0%
Server Player movement | 28 | 7 |  |  | 0%
Player Absorbtion | 35 | 5 |  |  | 0%
Server Sends update data to client | 28 | 2 |  |  | 0%
Client render game | 21 | 7 |  |  | 0%
Client Art | 19 | 2 |  |  | 0%